## Sheet1
MILESTONES
No | Features | Start Date | Deadline | Assign to | Status | Date Upload | Comment
1 | Login – Logout | 2019-05-22 | 2019-05-02 | Mikael | PROCESS...
2 | Manage Main Menu | 2019-05-22 | 2019-05-27 | Mikael, Yedija | PROCESS...
3 | Manage Product | 2019-05-22 | 2019-05-27 | Dhimas | PROCESS...
4 | Manage Facilities | 2019-05-22 | 2019-05-27 | Dhimas, Yedija | PROCESS...
5 | Manage Credit Simulations | 2019-05-22 | 2019-05-27 | Dhimas | PROCESS...
6 | Website | 2019-05-22 | 2019-05-27 | Dhimas, Mikael | PROCESS...
7 | App – Share | 2019-05-22 | 2019-05-27 | Dhimas, Mikael, | PROCESS...
8 | Manage Contact Menu | 2019-05-22 | 2019-05-27 | Yedija, Mikael | PROCESS...